## Month 1 — SOC Project
KHUSHBU JALAN: Cloud-Native Autonomous SOC & Threat Intelligence System
Semester 1 — Month 1 ¦ 31 Mar – 24 Apr 2026 ¦ Working Days: Monday – Friday ¦ Research + Tool Setup + All 9 Rubric Items
WEEK 1 ¦ 31 Mar – 3 Apr 2026 ¦ Target: R1c ✅ + R2a ✅ = 22% Rubric Complete
Name | Subitems | Person | Status | Date | Notes / What To Do | Evidence File
Sign Up: Oracle Cloud Free Tier Account | Infrastructure Setup | Khushbu Jalan | Not Started | 2026-03-31 | Go to oracle.com/cloud/free → sign up with your email → verify email → add credit card (verification only — not charged) → IMPORTANT: choose your Home Region carefully, this cannot be changed later → wait for activation email (up to 30 min) → login to console.oracle.com → note your Tenancy OCID (Identity → Tenancy → copy OCID). | OCI Console accessible ¦ Tenancy OCID saved in notes
Create GitHub Repo 'autonomous-cloud-soc' + Sign Up AbuseIPDB | Infrastructure Setup | Khushbu Jalan | Not Started | 2026-03-31 | GitHub: github.com → New Repository → Name: autonomous-cloud-soc → Private → Add README → Clone locally → create folders: /docs /scripts /evidence /configs /research → git add . && git commit -m 'Initial structure' && git push. AbuseIPDB: abuseipdb.com → Create Account → User Settings → API → Create Key (name: soc-project) → save API key securely in local notes file. | GitHub repo with 5 folders ¦ AbuseIPDB API key saved securely
Read All Project Documents + Create Project Notes | Research & Planning | Khushbu Jalan | Not Started | 2026-03-31 | Read every document: DESIGN_DOCUMENT_PRO_2.docx (highlight tech stack + architecture), WEEK_DAY_WISE details, rubric_1, rubric_2. For EACH rubric item write: what exactly do I need to submit? What does 'Complete' look like? Can this be done in Semester 1 or only Semester 2? Create /research/Project_Notes.md with your own words describing the full SOC pipeline: Windows Honeypot → Wazuh SIEM → n8n SOAR → AbuseIPDB check → OCI NSG block → Grafana dashboard. | research/Project_Notes.md committed ¦ all rubric items annotated
Install VS Code + Python 3.11 + Git + pycryptodome + Docker Desktop | Infrastructure Setup | Khushbu Jalan | Not Started | 2026-04-01 | VS Code: code.visualstudio.com → install Python extension + GitLens. Python 3.11: python.org → check 'Add to PATH'. Git: git-scm.com → git config --global user.name + user.email. Run: pip install pycryptodome → verify: pip show pycryptodome. Docker Desktop: docker.com → install → restart → docker --version → docker run hello-world. Watch 'Docker for beginners' on YouTube (30 min). Create /research/Docker_Concepts.md explaining Docker vs VM and why we use it. | python --version works ¦ pip show pycryptodome ok ¦ docker run hello-world passes ¦ Docker_Concepts.md committed
Install VirtualBox + Kali Linux VM + Research Wazuh / n8n / Grafana | Infrastructure Setup | Khushbu Jalan | Not Started | 2026-04-01 | VirtualBox: virtualbox.org → install. Kali ISO: kali.org/get-kali → Installer 64-bit (~3.5 GB, start download now). Create Kali VM: New → Linux/Debian 64 → 4096 MB RAM → 50 GB disk → attach ISO → install → boot to desktop → sudo apt update && sudo apt upgrade -y. Research tools: Wazuh (wazuh.com/platform) — SIEM, agent vs manager, Event ID 4625. n8n — SOAR, webhooks. Grafana — dashboards. Create /research/Tool_Overview.md with one section per tool and the data flow diagram. | Kali boots to desktop ¦ research/Tool_Overview.md committed with 3 tool sections + data flow
🏆 R1c — Write & Run AES-256 + SHA-256 Encryption Demo | RUBRIC 1c ¦ Encryption Techniques | Khushbu Jalan | Not Started | 2026-04-02 | Create scripts/encrypt_demo.py: from Crypto.Cipher import AES, from Crypto.Util.Padding import pad unpad, from Crypto.Random import get_random_bytes, import hashlib base64. Write: (1) generate 32-byte key + 16-byte IV (2) AES-256-CBC encrypt plaintext message (3) decrypt ciphertext back (4) verify decrypted matches original (5) SHA-256 hash of same plaintext (6) print all 4 values. Run script → screenshot terminal showing: Plaintext / Ciphertext / Decrypted / SHA-256. Save evidence/R1c_encryption_screenshot.png → git commit -m 'R1c COMPLETE — AES-256 + SHA-256 demo' && git push. | scripts/encrypt_demo.py + evidence/R1c_encryption_screenshot.png committed to GitHub ✅
Research: Brute-Force, Malware, Phishing + MITRE ATT&CK APT29 | Research & Planning | Khushbu Jalan | Not Started | 2026-04-02 | Brute-force: credential stuffing vs dictionary attack vs password spraying, why RDP 3389 is dangerous, Event ID 4625 vs 4624. Malware: types (virus/worm/trojan/ransomware), how VirusTotal works, behavioral analysis. Phishing: what is SET, how credential harvesters work. MITRE ATT&CK: go to attack.mitre.org → Groups → APT29 → find T1078 (Valid Accounts), T1021.001 (RDP), T1110 (Brute Force). Open attack-navigator → New Layer → highlight these 3 → Export JSON → save evidence/R2a_MITRE_APT29.json + screenshot. Create /research/Threat_Research_Notes.md. | research/Threat_Research_Notes.md committed ¦ evidence/R2a_MITRE_APT29.json + screenshot committed
🏆 R2a — Threat Analysis: VirusTotal + SET Phishing + ATT&CK Report | RUBRIC 2a ¦ Identify & Analyze Cyber Threats | Khushbu Jalan | Not Started | 2026-04-03 | Part A VirusTotal: virustotal.com → Search → paste hash: 44d88612fea8a8f36de82e1278abb02f (EICAR test, safe) → screenshot results showing detection ratio + AV engine names + behavioral indicators → save evidence/R2a_VirusTotal_screenshot.png. Part B SET: open Kali VM → sudo setoolkit → 1 (Social Engineering Attacks) → 2 (Website Attack Vectors) → 3 (Credential Harvester) → 2 (Site Cloner) → URL: http://testphp.vulnweb.com → open browser http://127.0.0.1 → screenshot cloned page → save evidence/R2a_SET_screenshot.png. Part C: write docs/R2a_Threat_Analysis.docx with 3 sections: malware findings, phishing description, APT29 ATT&CK mapping. | evidence/R2a_VirusTotal_screenshot.png evidence/R2a_SET_screenshot.png docs/R2a_Threat_Analysis.docx All committed ✅
31 Mar 2026 to 03 Apr 2026
WEEK 2 ¦ 6 Apr – 10 Apr 2026 ¦ Target: R1a ✅ + R1b ✅ + R1d ✅ = 55% Rubric Complete
Name | Subitems | Person | Status | Date | Notes / What To Do | Evidence File
OCI: Create VCN + Subnet + Internet Gateway + Security Rules | Infrastructure Setup | Khushbu Jalan | Not Started | 2026-04-06 | OCI Console → Networking → VCN → Create: Name=soc-vcn, CIDR=10.0.0.0/16. Inside VCN: Subnets → Create public-subnet 10.0.0.0/24. Internet Gateways → Create soc-igw. Route Table → Add rule: 0.0.0.0/0 → soc-igw. Security List: add 4 Ingress rules, ALL from YOUR PUBLIC IP/32 only: TCP 22 (SSH), TCP 443 (Wazuh Dashboard), TCP 5678 (n8n), TCP 3000 (Grafana). Screenshot VCN topology → save evidence/OCI_VCN_screenshot.png. | VCN + IGW + 4 security rules in OCI Console ¦ screenshot committed
OCI: Provision A1 Ampere VM (Ubuntu 22.04) + Swap + Docker | Infrastructure Setup | Khushbu Jalan | Not Started | 2026-04-06 | Compute → Instances → Create: Name=soc-manager, Image=Ubuntu 22.04, Shape=VM.Standard.A1.Flex → 4 OCPUs + 24 GB RAM, Assign public IPv4, Upload SSH public key (generate: ssh-keygen -t rsa -b 4096). Create → wait 5 min → note Public IP. SSH in. Add swap: sudo fallocate -l 4G /swapfile && sudo chmod 600 /swapfile && sudo mkswap /swapfile && sudo swapon /swapfile → free -h (confirm 4GB). Install Docker: sudo apt update && sudo apt install -y docker.io docker-compose && sudo usermod -aG docker ubuntu && docker run hello-world. | VM Running in OCI ¦ SSH works ¦ free -h shows 4GB swap ¦ docker hello-world passes
OS Hardening + Boot Snapshot + OCI API Key Setup | Infrastructure Setup | Khushbu Jalan | Not Started | 2026-04-07 | SSH hardening: sudo nano /etc/ssh/sshd_config → PasswordAuthentication no + PermitRootLogin no → sudo systemctl restart ssh. Firewall: sudo ufw allow 22 && sudo ufw allow 443 && sudo ufw enable → sudo ufw status (confirm active). Boot snapshot: OCI → Storage → Boot Volumes → Create Manual Backup → name 'week2-baseline'. OCI API Key: Identity & Security → Users → [your user] → API Keys → Add → Generate Key Pair → Download private key (.pem) → note fingerprint. NEVER commit .pem to GitHub. Create configs/oci_setup_notes.md with Tenancy OCID, region, user OCID, fingerprint. | ufw status: active ¦ boot snapshot created ¦ OCI API key downloaded ¦ configs/oci_setup_notes.md committed (no key in repo)
Research: Network Security Concepts — Ports, Firewalls, Event Logs | Research & Planning | Khushbu Jalan | Not Started | 2026-04-07 | What is a port? Why 3389=RDP, 22=SSH, 443=HTTPS, 80=HTTP, 445=SMB? What makes a port open vs closed vs filtered? What is a Network Security Group (NSG) / Security List — how does a deny rule block an attacker? What is Windows Event Viewer? Event ID 4625 (failed login) vs 4624 (successful login) — why are these critical for brute-force detection? Create /research/Network_Security_Notes.md with all answers in your own words. Connect each concept to how it applies to this SOC project. | research/Network_Security_Notes.md committed ¦ covers ports, firewalls, Windows Event IDs
🏆 R1a — Write Incident Response Plan (Research-Based) | RUBRIC 1a ¦ Incident Response Plan | Khushbu Jalan | Not Started | 2026-04-08 | Create docs/R1a_IRP.docx. Label it 'Semester 1 Plan — To Be Tested in Month 2 When Wazuh Is Live'. ATTACK TYPE: Brute-Force / Credential Stuffing — define it, give RDP example. PHASE 1 DETECT: Wazuh monitors Windows Event ID 4625, threshold 5 logins/60s = Level 10 HIGH alert, target detection <10 seconds. PHASE 2 CONTAIN: n8n receives Wazuh webhook → queries AbuseIPDB for IP reputation → if abuse score >50% → calls OCI API to add attacking IP to NSG Deny List, target <30 seconds from alert. PHASE 3 ERADICATE: verify block is active in OCI NSG → review Wazuh logs for lateral movement → check FIM for unauthorized file changes. PHASE 4 RECOVER: review blocked IP after 24h for false positives → remove block if legitimate → document incident in log → update detection rules if needed. | docs/R1a_IRP.docx: 4 phases + attack type + marked 'plan to test Month 2' ✅
🏆 R1b — Write Security Policy (3 Rules + CIA Triad) | RUBRIC 1b ¦ Comprehensive Security Policy | Khushbu Jalan | Not Started | 2026-04-08 | Create docs/R1b_Security_Policy.docx. RULE 1 — Access Control Policy: All management interfaces (SSH port 22, Wazuh Dashboard 443, n8n 5678, Grafana 3000) restricted to authorized IP addresses only via OCI Security Lists. Unauthorized access triggers automatic investigation. RULE 2 — Log Retention Policy: All security events retained minimum 14 days in Wazuh Indexer. After 14 days archived to OCI Object Storage for 90 days. Log deletion requires written approval. RULE 3 — Encryption Policy: All data in transit encrypted via TLS 1.2+. Sensitive configs (API keys, passwords) stored at rest using AES-256. Passwords hashed with SHA-256 minimum. CIA TRIAD: Confidentiality = OCI NSG restricts access to authorized users only. Integrity = Wazuh FIM monitors critical system files for unauthorized changes. Availability = 24/7 autonomous SOC pipeline ensures continuous monitoring uptime. | docs/R1b_Security_Policy.docx: 3 rules (Access/Log/Encryption) + CIA Triad section ✅
🏆 R1d — Legal & Ethical Compliance Section (Added to IRP) | RUBRIC 1d ¦ Legal & Ethical Compliance | Khushbu Jalan | Not Started | 2026-04-09 | Open docs/R1a_IRP.docx → Add Section 5: Legal and Ethical Compliance. LAW 1 — CFAA (18 U.S.C. §1030 Computer Fraud and Abuse Act): unauthorized access to computer systems is a federal crime punishable by fines and up to 10 years imprisonment. How our plan upholds it: all monitoring occurs only on OCI infrastructure we own and operate — no unauthorized systems accessed. LAW 2 — GDPR Article 33: data breach must be reported to supervisory authority within 72 hours of becoming aware. How our plan upholds it: detection phase provides immediate awareness enabling timely notification; 14-day log retention supports investigation. ETHICAL CONSIDERATION: Honeypot operates on our own infrastructure passively logging real internet attack traffic — no entrapment. Responsible disclosure: if real attacker identified, report to authorities — do not exploit, publish, or weaponize findings. | docs/R1a_IRP.docx Section 5 added: CFAA + GDPR Art.33 + ethical consideration ✅
Learn Nmap — Flags, Concepts + Run Practice Scan on scanme.nmap.org | Research & Planning | Khushbu Jalan | Not Started | 2026-04-09 | Read nmap.org/book/man.html (Port Scanning Overview section). Key flags: -sV (service version detection), -O (operating system detection), -A (aggressive: OS + version + scripts + traceroute), -p- (scan all 65535 ports), -oX (save as XML), -oN (save as text). What does open / closed / filtered mean? Install on Kali if needed: sudo apt install nmap. Run LEGAL practice scan on Nmap's official test target: nmap -sV -O scanme.nmap.org -oN evidence/R2b_practice_scan.txt → screenshot output → save evidence/R2b_practice_scan_screenshot.png → commit both. Create /research/R2b_Nmap_Command_Reference.md listing all commands to run on Honeypot + explanation. | evidence/R2b_practice_scan.txt + evidence/R2b_practice_scan_screenshot.png committed ¦ research/R2b_Nmap_Command_Reference.md committed
Research: Wazuh Deep Dive — Architecture, Rules, Alert Levels | Research & Planning | Khushbu Jalan | Not Started | 2026-04-10 | Read documentation.wazuh.com/current/getting-started. Study: agent → manager communication, what is ossec.conf, rules vs decoders, alert level scale 1-15 (Level 10=High severity), Wazuh Indexer (stores alerts as OpenSearch documents), Wazuh Dashboard (Kibana-based visualization). Watch 'Wazuh SIEM explained' on YouTube. Create /research/Wazuh_Deep_Dive.md: trace full data path Windows Event → Wazuh Agent → Wazuh Manager → alert generated → Wazuh Indexer → Dashboard. Include draft custom rule XML for brute-force: <rule id='100001' level='10' frequency='5' timeframe='60'>. Write 'Month 2 Deployment Steps' section listing exactly what you will do when deploying Wazuh. | research/Wazuh_Deep_Dive.md committed ¦ data flow + custom rule XML drafted ¦ Month 2 steps written
06 Apr 2026 to 10 Apr 2026
WEEK 3 ¦ 13 Apr – 17 Apr 2026 ¦ Target: R2b ✅ + R2c ✅ + R2d ✅ = 88% Rubric Complete
Name | Subitems | Person | Status | Date | Notes / What To Do | Evidence File
Install OpenCTI via Docker Compose on OCI VM | Infrastructure Setup | Khushbu Jalan | Not Started | 2026-04-13 | SSH into OCI VM → mkdir ~/opencti && cd ~/opencti → download docker-compose.yml from docs.opencti.io (Community Edition). Create .env file with: OPENCTI_ADMIN_EMAIL=admin@soc.local, OPENCTI_ADMIN_PASSWORD=YourSecurePass!, OPENCTI_ADMIN_TOKEN=[run: python3 -c 'import uuid; print(uuid.uuid4())']. Run: docker-compose up -d → wait 15 minutes for all services to initialize. Add TCP 8080 to OCI Security List (from YOUR IP only). Access http://[OCI_IP]:8080 → login → screenshot the OpenCTI dashboard → save evidence/R2c_OpenCTI_dashboard.png. | OpenCTI running at http://[OCI_IP]:8080 ¦ login works ¦ dashboard screenshot committed
🏆 R2c — Configure 2 Connectors + Add 2 IoCs in OpenCTI | RUBRIC 2c ¦ Threat Intelligence + OpenCTI | Khushbu Jalan | Not Started | 2026-04-13 | CONNECTOR 1 — MITRE ATT&CK: OpenCTI → Settings → Connectors → find MITRE ATT&CK connector → Enable → wait for first import → screenshot showing connector Active or Running status → save evidence/R2c_MITRE_connector.png. CONNECTOR 2 — AbuseIPDB: Settings → Connectors → AbuseIPDB → enter your AbuseIPDB API key → Enable → screenshot Active → save evidence/R2c_AbuseIPDB_connector.png. IoC 1: Analysis → Observables → + Create → Type: IPv4 Address → enter known malicious IP from abuseipdb.com top abusers → Labels: Brute-Force + Malicious. IoC 2: + Create → Type: File (SHA256) → value: 44d88612fea8a8f36de82e1278abb02f → Labels: Malware + EICAR-Test. Screenshot both IoCs in Observables list → save evidence/R2c_IoCs_screenshot.png. | evidence/R2c_OpenCTI_dashboard.png evidence/R2c_MITRE_connector.png evidence/R2c_AbuseIPDB_connector.png evidence/R2c_IoCs_screenshot.png All committed ✅
Research: Risk Management Concepts + Draft Risk Register | Research & Planning | Khushbu Jalan | Not Started | 2026-04-14 | Research: what is a risk register? CVSS scoring scale: Critical 9-10, High 7-8.9, Medium 4-6.9, Low 0-3.9. How to calculate risk level: Likelihood × Impact. Read Design Doc risks section: Self-Lockout, Resource Crash, Storage Bloat, Account Reclamation. Identify 2 Critical risks for your SOC: Risk 1 = Open RDP Port 3389 exposed to internet (MITRE T1021.001, Likelihood HIGH, Impact CRITICAL). Risk 2 = Credential Brute-Force attack possible (MITRE T1110, Likelihood HIGH, Impact HIGH). Create /research/Risk_Management_Notes.md with full analysis — this becomes your R2d draft. | research/Risk_Management_Notes.md committed ¦ 2 critical risks with MITRE IDs analyzed
🏆 R2b — Vulnerability Assessment Plan + Practice Scan Analysis | RUBRIC 2b ¦ Vulnerability Assessment | Khushbu Jalan | Not Started | 2026-04-14 | Create docs/R2b_Vulnerability_Assessment_Plan.docx. SECTION 1: What is a vulnerability scan? Difference from penetration testing. SECTION 2: All Nmap commands to run on the Honeypot with full explanations: nmap -sV -O -A -p- [Honeypot_IP] -oX nmap_scan.xml — explain every flag, expected run time 5-20 min, what the XML output contains. SECTION 3: What to look for — port 3389 open = CRITICAL (RDP internet-exposed), port 445 = HIGH (SMB), port 80/8080 = MEDIUM, OS Windows Server → search NVD for known CVEs. SECTION 4: Asset inventory template with expected Honeypot values pre-filled. SECTION 5: Paste and analyse the scanme.nmap.org practice scan output — classify each finding as Critical/High/Medium/Low. | docs/R2b_Vulnerability_Assessment_Plan.docx committed Includes practice scan analysis ✅
Kali Linux Skills Practice — Security Toolkit Exploration | Learning & Skills | Khushbu Jalan | Not Started | 2026-04-15 | Open Kali VM. Terminal practice: ls, cd, pwd, mkdir, cat, grep, nano, chmod, chown, sudo, pipes (¦), redirection (>). Network commands: ifconfig / ip addr (see your IP), ping google.com, netstat -tulnp (listening ports), traceroute google.com. Browse Applications menu — read about each tool category: Information Gathering (Nmap, Netdiscover), Vulnerability Analysis, Web Application Analysis (Nikto, Burp Suite), Password Attacks (Hydra, John the Ripper), Social Engineering (SET). Create /research/Kali_Tools_Overview.md: list 10 tools, what each does, when used ethically, which ones relate to this project. | research/Kali_Tools_Overview.md committed ¦ 10 tools documented with ethical use cases
🏆 R2d — Write Risk Register + Risk Monitoring SOP | RUBRIC 2d ¦ Risk Management | Khushbu Jalan | Not Started | 2026-04-15 | Using your Risk_Management_Notes.md draft. Create docs/R2d_Risk_Register.docx: CRITICAL RISK 1 = Open RDP Port 3389 Exposed to Internet (MITRE T1021.001) → Likelihood: HIGH ¦ Impact: CRITICAL ¦ Current Control: Wazuh Event 4625 monitoring + n8n auto-block (Month 2) ¦ Residual Risk: LOW. CRITICAL RISK 2 = Credential Brute-Force Attack (MITRE T1110) → Likelihood: HIGH ¦ Impact: HIGH ¦ Current Control: 5-login/60s threshold alert + automatic IP ban ¦ Residual Risk: LOW. Create docs/R2d_Monitoring_SOP.docx: DAILY check Wazuh dashboard alert count ¦ WEEKLY review OCI NSG blocked IP list + disk usage <80% ¦ MONTHLY re-run Nmap scan on Honeypot + update Risk Register entries. | docs/R2d_Risk_Register.docx: 2 critical risks (T1021 + T1110) docs/R2d_Monitoring_SOP.docx: daily/weekly/monthly schedule ✅
Research: n8n SOAR + Grafana Dashboard Planning for Month 2 | Research & Planning | Khushbu Jalan | Not Started | 2026-04-16 | n8n (n8n.io/workflows + docs.n8n.io): understand Webhook node (receives POST requests), HTTP Request node (calls external APIs like AbuseIPDB and OCI), IF node (conditional logic gate), Set node (transforms data). Plan your 5-node workflow: (1) Webhook receives Wazuh alert JSON → (2) IF node: is src_ip == my_home_ip? (whitelist check, stop if yes) → (3) HTTP Request: AbuseIPDB API check → (4) IF node: abuseConfidenceScore > 50? → (5) HTTP Request: OCI NSG Add Deny Rule. Create /research/n8n_Workflow_Plan.md with node diagram. Grafana: plan 4 dashboard panels (World map, Total alerts, Top IPs, Severity chart). Create /research/Grafana_Dashboard_Plan.md. | research/n8n_Workflow_Plan.md + research/Grafana_Dashboard_Plan.md committed
Week 3 Full Commit + GitHub Tag week3 | Validation | Khushbu Jalan | Not Started | 2026-04-16 | VERIFY ALL: docs/R1d IRP Section 5 ✓ ¦ evidence/R2c_* 4 screenshots ✓ ¦ docs/R2b_Vulnerability_Assessment_Plan.docx ✓ ¦ docs/R2d_Risk_Register.docx ✓ ¦ docs/R2d_Monitoring_SOP.docx ✓ ¦ OpenCTI running ✓ ¦ all research docs ✓. Run: git add . && git commit -m 'Week 3 complete — 8 rubrics done' && git push && git tag -a week3 -m '88% rubric complete' && git push origin week3. | All files on GitHub ¦ tag 'week3' created ¦ 88% rubric complete
13 Apr 2026 to 17 Apr 2026
WEEK 4 ¦ 20 Apr – 24 Apr 2026 ¦ Target: R2e ✅ = 100% ALL 9 RUBRICS DONE 🎉
Name | Subitems | Person | Status | Date | Notes / What To Do | Evidence File
🏆 R2e — Write Security Monitoring Use Case + Simulated IR Scenario | RUBRIC 2e ¦ Security Monitoring & Incident Response | Khushbu Jalan | Not Started | 2026-04-20 | Create docs/R2e_Use_Case.docx: USE CASE NAME Brute-Force Detection & Auto-Block. DETECTION RULE: IF Windows Event ID 4625 fires ≥5 times in 60 seconds THEN trigger Wazuh Level 10 HIGH alert. ALERT PRIORITIZATION TABLE: Level 10 = immediate automated response (n8n blocks IP), Level 7-9 = investigate within 1 hour, Level 1-6 = log and review daily. RESPONSE PROCEDURE (5 steps): Step 1 Wazuh alert fires → n8n webhook triggered. Step 2 whitelist check (stop if your own IP). Step 3 AbuseIPDB score checked. Step 4 if score >50% OCI NSG deny rule added. Step 5 Grafana attack map updates. Create docs/R2e_IR_Scenario.docx with SIMULATED timeline (this is a planned scenario, not yet live): T+0s bot sends 5 failed RDP logins from IP 185.220.101.x → T+8s Wazuh Level 10 alert generated → T+12s n8n workflow triggered → T+16s AbuseIPDB returns score 94% → T+22s OCI NSG deny rule added, IP blocked. INCIDENT CLASSIFICATION: Brute-Force Attack, HIGH severity. LESSONS LEARNED: (1) Whitelist check essential to prevent self-lockout. (2) AbuseIPDB significantly reduces false positives. (3) Target 30-second remediation is achievable with automation. | docs/R2e_Use_Case.docx: detection rule + alert priority + 5-step procedure docs/R2e_IR_Scenario.docx: timeline + classification + lessons learned ✅
Final Month 1 Audit — All 9 Rubric Evidence Files Verified | Final Audit | Khushbu Jalan | Not Started | 2026-04-21 | Open GitHub and verify every file exists and is complete: R1c = scripts/encrypt_demo.py + evidence/R1c_encryption_screenshot.png ✓ ¦ R1a = docs/R1a_IRP.docx (4 phases + attack type) ✓ ¦ R1b = docs/R1b_Security_Policy.docx (3 rules + CIA Triad) ✓ ¦ R1d = R1a_IRP.docx Section 5 (CFAA + GDPR + ethical) ✓ ¦ R2a = docs/R2a_Threat_Analysis.docx + 3 evidence files (VirusTotal + SET + MITRE) ✓ ¦ R2b = docs/R2b_Vulnerability_Assessment_Plan.docx + practice scan ✓ ¦ R2c = 4 OpenCTI screenshots ✓ ¦ R2d = docs/R2d_Risk_Register.docx + docs/R2d_Monitoring_SOP.docx ✓ ¦ R2e = docs/R2e_Use_Case.docx + docs/R2e_IR_Scenario.docx ✓. Create evidence/Evidence_Index.md listing every file name + which rubric item it satisfies. | evidence/Evidence_Index.md committed ¦ all 9 rubric items verified present and complete
Verify OCI Billing = $0.00 + Create Evidence ZIP Package | Final Delivery | Khushbu Jalan | Not Started | 2026-04-22 | Verify OCI billing: OCI Console → Billing & Cost Management → Cost Analysis → confirm total = $0.00 → screenshot → save evidence/KPI_zero_cost.png → commit. Create ZIP: cd path/to/autonomous-cloud-soc && zip -r DAE_SOC_Semester1_Evidence.zip docs/ evidence/ scripts/ → verify zip opens correctly → commit to GitHub. Check OpenCTI is still running (docker ps on OCI VM). Double-check all evidence file names match Evidence_Index.md exactly. | evidence/KPI_zero_cost.png committed ¦ DAE_SOC_Semester1_Evidence.zip committed ¦ OCI bill $0 confirmed
GitHub Release v1.0 + Month 1 Reflection — ALL DONE 🎉 | Final Delivery | Khushbu Jalan | Not Started | 2026-04-22 | Create GitHub Release: git add . && git commit -m 'ALL 9 RUBRICS COMPLETE — Month 1 Semester 1 Final' && git push && git tag -a v1.0 -m 'All 9 rubrics complete — Semester 1 done' && git push origin v1.0. On GitHub: Releases → Create new release → select tag v1.0 → attach DAE_SOC_Semester1_Evidence.zip → publish. Write /research/Month1_Reflection.md: what did you learn? What cybersecurity concepts are now clear? What questions do you still have? What will you do differently in Month 2 when live tools are deployed? | GitHub Release v1.0 published with evidence ZIP ¦ research/Month1_Reflection.md committed 🎉
Month 2 Deployment Prep — Research Wazuh Docker Stack | Research & Planning | Khushbu Jalan | Not Started | 2026-04-23 | Start researching for Month 2 live deployment. Study the Wazuh docker-compose.yml structure: 3 containers (wazuh-manager, wazuh-indexer, wazuh-dashboard), what ports each uses (1514 for agent, 1515 enrollment, 9200 Indexer, 443 Dashboard), what volumes they need, what SSL certificate generation involves. Download and read the official Wazuh Docker Compose file from packages.wazuh.com. Create /research/Wazuh_Docker_Plan.md: the EXACT steps you will follow to deploy Wazuh in Month 2, including pre-planned docker-compose.yml content. | research/Wazuh_Docker_Plan.md committed ¦ Month 2 Wazuh deployment steps fully planned
20 Apr 2026 to 24 Apr 2026
🎉 MONTH 1 COMPLETE ¦ ALL 9 RUBRIC ITEMS DONE ¦ Research Portfolio Ready ¦ OpenCTI Deployed ¦ GitHub Release v1.0 Tagged