## khushbu jalan cloud- naive auto
KHUSHBU JALAN: Cloud- Naive Autonomous SOC &Threat Intelligence System
Phase 1: Foundations & Infrastructure (Weeks 1–3)
Name | Subitems | Person | Status | Date | Notes
WEEK 1 |  | KHUSHBU JALAN
OCI Tenancy Setup & Networking |  | KHUSHBU JALAN |  | 2026-03-16 | Create VCN, Subnets, and IGW
Provision A1 Ampere Instance |  | KHUSHBU JALAN |  | 2026-03-17 | 4 OCPUs, 24GB RAM, Ubuntu 22.04
Docker & Environment Hardening |  | KHUSHBU JALAN |  | 2026-03-18 | Install Docker/Compose; Set up Swap File
Buffer: Security Group Config |  | KHUSHBU JALAN |  | 2026-03-19 | Ensure SSH is restricted to your IP
2026-03-16 to 2026-03-19
week 2
Name | Subitems | Person | Status | Date | Notes
Windows Honeypot Deployment |  | KHUSHBU JALAN |  | 2026-03-23 | Provision Windows Server VM (Free Tier)
Honeypot "Weakening" |  | KHUSHBU JALAN |  | 2026-03-24 | Open RDP (3389) to the Public Internet
Initial Telemetry Check |  | KHUSHBU JALAN |  | 2026-03-25 | Verify Event Viewer is recording failed logins
Buffer: OS Updates & Snapshots |  | KHUSHBU JALAN |  | 2026-03-26
2026-03-23 to 2026-03-26
WEEK 3
Name | Subitems | Person | Status | Date | Notes
OCI API & CLI Configuration |  | KHUSHBU JALAN |  | 2026-03-30 | Create API Key for n8n to talk to OCI
Infrastructure Validation |  | KHUSHBU JALAN |  | 2026-03-31 | Test connectivity between Windows and Linux
Documentation: Network Map |  | KHUSHBU JALAN |  | 2026-04-01 | Map out IP flow and Port requirements
Buffer: Troubleshooting |  | KHUSHBU JALAN |  | 2026-04-02 | Address any OCI "Out of Capacity" errors
2026-03-30 to 2026-04-02
Phase 2: Detection (Weeks 4–6)
Name | Subitems | Person | Status | Date | Notes
Wazuh Manager Installation |  | KHUSHBU JALAN |  | 2026-05-04 | Deploy Wazuh via Docker Compose
SSL & Dashboard Setup |  | KHUSHBU JALAN |  | 2026-05-05 | Configure HTTPS certificates for Wazuh
Wazuh Agent Deployment |  | KHUSHBU JALAN |  | 2026-05-06 | Install agent on Windows Honeypot
Buffer: Agent Connectivity |  | KHUSHBU JALAN |  | 2026-05-07 | Verify "Active" status in Wazuh Manager
Syslog & Event Collection |  | KHUSHBU JALAN |  | 2026-05-11 | Configure ossec.conf for Windows Events
Custom Rule Creation |  | KHUSHBU JALAN |  | 2026-05-12 | Define threshold: 5 failed logins = High Alert
Log Retention Policies |  | KHUSHBU JALAN |  | 2026-05-13 | Configure Indexer to prune logs (14 days)
Buffer: Rule Testing |  | KHUSHBU JALAN |  | 2026-05-14 | Trigger manual failures to test alerts
File Integrity Monitoring (FIM) |  | KHUSHBU JALAN |  | 2026-05-18 | Monitor C:\Windows\System32 for changes
Vulnerability Detection |  | KHUSHBU JALAN |  | 2026-05-19 | Enable Wazuh's vulnerability scanner module
Baseline Dashboarding |  | KHUSHBU JALAN |  | 2026-05-20 | Clean up default Wazuh dashboard views
Buffer: Resource Monitoring |  | KHUSHBU JALAN |  | 2026-05-21 | Check RAM usage of the Indexer/Dashboard
2026-05-04 to 2026-05-21
Phase 3: Response & Automation (Weeks 7–9)
Name | Subitems | Person | Status | Date | Notes
n8n Self-Hosted Deployment |  | KHUSHBU JALAN |  | 2026-05-25 | Deploy n8n via Docker on the OCI instance
n8n Initial Config |  | KHUSHBU JALAN |  | 2026-05-26 | Set up User Auth and Webhook URL
Wazuh Integration Script |  | KHUSHBU JALAN |  | 2026-05-27 | Write Python script to push alerts to n8n
Buffer: Webhook Connectivity |  | KHUSHBU JALAN |  | 2026-05-28 | Write Python script to push alerts to n8n Ensure Wazuh can "reach" n8n internally
2026-05-25 to 2026-05-28
WEEK 8
Name | Subitems | Person | Status | Date | Notes
Enrichment: AbuseIPDB API |  | KHUSHBU JALAN |  | 2026-06-01 | Add IP reputation check node in n8n
Logic Gate: Threat Scoring |  | KHUSHBU JALAN |  | 2026-06-02 | Only block if Abuse Score > 50%
OCI Remediation Node |  | KHUSHBU JALAN |  | 2026-06-03 | Build the "Update NSG" API call in n8n
Buffer: Whitelist Safety |  | KHUSHBU JALAN |  | 2026-06-04 | CRITICAL: Build the "My IP" exclusion
2026-06-01 to 2026-06-04
WEEK 9
Name | Subitems | Person | Status | Date | Notes
Full Loop Test: Brute Force |  | KHUSHBU JALAN |  | 2026-06-08 | Attempt attack -> Verify n8n triggers block
Debugging Latency |  | KHUSHBU JALAN |  | 2026-06-09 | Optimize Python script and n8n execution time
Error Handling |  | KHUSHBU JALAN |  | 2026-06-10 | Set up n8n notifications for failed workflows
Buffer: Remediation Testing |  | KHUSHBU JALAN |  | 2026-06-11 | Ensure the IP is actually dropped by OCI
2026-06-08 to 2026-06-11
Phase 4: Visualization & Optimization (Weeks 10–12)
Name | Subitems | Person | Status | Date | Notes
Grafana Installation |  | KHUSHBU JALAN |  | 2026-06-15 | Add Grafana container to the stack
Data Source Connection |  | KHUSHBU JALAN |  | 2026-06-16 | Connect Grafana to Wazuh (Indexer/OpenSearch)
Geospatial Mapping |  | KHUSHBU JALAN |  | 2026-06-17 | Create "Attack World Map" based on IP logs
Buffer: Dashboard Polish |  | KHUSHBU JALAN |  | 2026-06-18 | Fix color coding and refresh rates
2026-06-15 to 2026-06-18
WEEK 11
Name | Subitems | Person | Status | Date | Notes
Stress Testing |  | KHUSHBU JALAN |  | 2026-06-21 | Simulate 100+ requests to check CPU spikes
Feature: Canary Tokens |  | KHUSHBU JALAN |  | 2026-06-22 | Place "fake" creds to detect human intruders
Multi-Vector Rules |  | KHUSHBU JALAN |  | 2026-06-23 | Add rules for PowerShell execution/malware
Buffer: System Hardening |  | KHUSHBU JALAN |  | 2026-06-24 | Finalize firewall rules for the SOC itself
2026-06-21 to 2026-06-24
FINAL WEEK 12
Name | Subitems | Person | Status | Date | Notes
Final Project Review |  | KHUSHBU JALAN |  | 2026-06-29 | Audit against "Zero Cost" & "30s Latency"
Export Configuration |  | KHUSHBU JALAN |  | 2026-06-30 | Export n8n JSONs and Grafana Dashboards
Final Documentation |  | KHUSHBU JALAN |  | 2026-07-01 | Record "How-To" for future maintenance
PROJECT COMPLETION |  | KHUSHBU JALAN |  | 2026-07-02 | COMPLETE
2026-06-29 to 2026-07-02