## Month 1 — Semester 1 Plan
KHUSHBU JALAN: Cloud-Native Autonomous SOC & Threat Intelligence System
Semester 1 — Month 1 Plan ¦ 31 Mar – 23 Apr 2026 ¦ Research, Reports & Tool Setup ¦ All 9 Rubrics by Week 4
Month 1 — Semester 1: Learn Concepts → Research → Install Tools → Write Rubric Reports
WEEK 1 ¦ 30 Mar – 2 Apr 2026 ¦ 🎯 Target: R1c + R2a Complete = 22% Rubric
Name | Subitems / Rubric Tag | Person | Status | Date | Notes / What to Do | Evidence File
Sign Up: Oracle Cloud Free Tier Account | Infrastructure Setup | KHUSHBU JALAN | Not Started | 2026-03-30 | Go to oracle.com/cloud/free → sign up → verify email → add credit card (verification only, not charged) → choose Home Region carefully (cannot change later) → wait for activation → note Tenancy OCID from Identity > Tenancy | OCI Console accessible; Tenancy OCID saved
Create GitHub Repository: 'autonomous-cloud-soc' | Infrastructure Setup | KHUSHBU JALAN | Not Started | 2026-03-30 | github.com → New Repo → Name: autonomous-cloud-soc → Private → Add README → Clone locally → Create folders: /docs /scripts /evidence /configs /research → git add . && git commit -m 'Initial structure' && git push | GitHub repo live with 5 folders
Sign Up: AbuseIPDB Free API Key | Infrastructure Setup | KHUSHBU JALAN | Not Started | 2026-03-30 | abuseipdb.com → Create Account → User Settings → API → Create Key (name: soc-project) → save API key securely in notes. Explore site: search sample IPs, understand 'abuseConfidenceScore' (0-100%) | AbuseIPDB account + API key saved
Read & Annotate All Project Documents | Research & Planning | KHUSHBU JALAN | Not Started | 2026-03-30 | Read: DESIGN_DOCUMENT_PRO_2.docx, WEEK_DAY_WISE_PROJECT_DETAILS.docx, rubric_1, rubric_2. For each rubric item write: what to submit, what 'complete' looks like. Create /research/Project_Notes.md with SOC architecture diagram: Windows Honeypot → Wazuh → n8n → OCI Block → Grafana | research/Project_Notes.md committed
Install VS Code + Python 3.11 + Git + pycryptodome | Infrastructure Setup | KHUSHBU JALAN | Not Started | 2026-03-31 | VS Code: code.visualstudio.com → install Python + GitLens extensions. Python 3.11: python.org → check 'Add to PATH'. Git: git-scm.com → set name/email. Run: pip install pycryptodome → verify: pip show pycryptodome | python --version works; pip show pycryptodome shows info
Install VirtualBox + Download Kali Linux ISO | Infrastructure Setup | KHUSHBU JALAN | Not Started | 2026-03-31 | VirtualBox: virtualbox.org → install. Kali ISO: kali.org/get-kali → Installer 64-bit (~3.5 GB, start download now!). Create Kali VM: New → Linux/Debian 64 → 4096 MB RAM → 50 GB disk → attach ISO → install → boot to desktop → sudo apt update && sudo apt upgrade -y | Kali Linux VM boots to desktop; terminal opens
Install Docker Desktop + Learn Docker Concepts | Infrastructure Setup | KHUSHBU JALAN | Not Started | 2026-03-31 | Docker Desktop: docker.com → install → restart → verify: docker --version → docker run hello-world (read output carefully). Research: what is a container vs VM? What is docker-compose? Create /research/Docker_Concepts.md: explain Docker in your own words, why we use it for this project | docker run hello-world succeeds; Docker_Concepts.md committed
Research: Wazuh, n8n, Grafana — Tool Overview | Research & Planning | KHUSHBU JALAN | Not Started | 2026-03-31 | Wazuh (wazuh.com/platform): What is SIEM? How do agents talk to manager? What is Event ID 4625? What is alert Level 10? n8n (n8n.io): What is SOAR? How does a webhook work? Grafana: what is a SOC dashboard? Create /research/Tool_Overview.md with one section per tool + data flow diagram | research/Tool_Overview.md committed with 3 tool sections
🏆 R1c — Write & Run AES-256 + SHA-256 Encryption Demo | RUBRIC 1c ¦ Encryption Techniques | KHUSHBU JALAN | Not Started | 2026-04-01 | Create scripts/encrypt_demo.py using pycryptodome: AES-256-CBC encrypt plaintext → ciphertext → decrypt back → verify match. Add SHA-256 hash of same plaintext. Run script → screenshot terminal showing all 4 lines. Save as evidence/R1c_encryption_screenshot.png → git commit -m 'R1c COMPLETE' | scripts/encrypt_demo.py + evidence/R1c_encryption_screenshot.png committed ✅
Research: Brute-Force & Malware Concepts (prep for R2a + R1a) | Research & Planning | KHUSHBU JALAN | Not Started | 2026-04-01 | Brute-Force: what is credential stuffing vs dictionary attack vs password spraying? Why is RDP 3389 dangerous? What is Event ID 4625? Malware: types (virus/worm/trojan/ransomware), behavioral analysis, how VirusTotal works. Phishing: what is a credential harvester, what is SET? Create /research/Threat_Research_Notes.md | research/Threat_Research_Notes.md committed
Explore MITRE ATT&CK Framework + Create APT29 Navigator Layer | Research & Planning | KHUSHBU JALAN | Not Started | 2026-04-01 | Go to attack.mitre.org → Groups → APT29. Find techniques: T1078 (Valid Accounts), T1021.001 (RDP), T1110 (Brute Force). Open mitre-attack.github.io/attack-navigator → New Layer → highlight those 3 techniques in red → Export as JSON → save evidence/R2a_MITRE_APT29.json + screenshot | evidence/R2a_MITRE_APT29.json + screenshot committed
🏆 R2a — Threat Analysis: VirusTotal + SET Phishing + ATT&CK Mapping | RUBRIC 2a ¦ Identify & Analyze Cyber Threats | KHUSHBU JALAN | Not Started | 2026-04-02 | Part A: virustotal.com → Search hash 44d88612fea8a8f36de82e1278abb02f (EICAR test) → screenshot detection results → save R2a_VirusTotal_screenshot.png. Part B: Kali VM → sudo setoolkit → 1 → 2 → 3 → 2 → clone testphp.vulnweb.com → screenshot phishing page → save R2a_SET_screenshot.png. Write docs/R2a_Threat_Analysis.docx: 3 sections (malware/phishing/APT29) | evidence/R2a_VirusTotal_screenshot.png evidence/R2a_SET_screenshot.png docs/R2a_Threat_Analysis.docx committed ✅
Week 1 Validation — All Tools Working + Evidence Checklist | Validation | KHUSHBU JALAN | Not Started | 2026-04-02 | Verify: python --version ✓, pip show pycryptodome ✓, docker run hello-world ✓, Kali boots ✓, OCI Console accessible ✓, GitHub repo has 5 folders ✓, AbuseIPDB API key saved ✓. Create evidence/Week1_Checklist.md with all boxes checked. git commit -am 'Week 1 complete — 2 rubrics done (R1c + R2a)' && git push | Week1_Checklist.md committed; GitHub shows all files
30 Mar 2026 to 02 Apr 2026
WEEK 2 ¦ 6 Apr – 9 Apr 2026 ¦ 🎯 Target: R1a + R1b + R1d + R2b Complete = 66% Rubric
Name | Subitems / Rubric Tag | Person | Status | Date | Notes / What to Do | Evidence File
OCI: Create VCN + Subnet + Internet Gateway + Security Lists | Infrastructure Setup | KHUSHBU JALAN | Not Started | 2026-04-06 | OCI Console → Networking → VCN → Create: Name soc-vcn, CIDR 10.0.0.0/16. Add public subnet 10.0.0.0/24. Create Internet Gateway: soc-igw. Route Table: 0.0.0.0/0 → IGW. Security List — Add 4 ingress rules (all from YOUR IP/32): TCP 22 (SSH), TCP 443 (Wazuh), TCP 5678 (n8n), TCP 3000 (Grafana). Screenshot VCN topology. | VCN + IGW + 4 security rules visible in OCI Console; screenshot committed
OCI: Provision A1 Ampere VM (Ubuntu 22.04) — The SOC Brain | Infrastructure Setup | KHUSHBU JALAN | Not Started | 2026-04-06 | Compute → Instances → Create: Name soc-manager, Image Ubuntu 22.04, Shape VM.Standard.A1.Flex → 4 OCPUs + 24 GB RAM, Assign public IPv4, Upload SSH public key. Click Create → wait 5 min → note Public IP. Test: ssh -i ~/.ssh/soc_key ubuntu@[IP]. Add 4GB swap: sudo fallocate -l 4G /swapfile && sudo chmod 600 /swapfile && sudo mkswap /swapfile && sudo swapon /swapfile → free -h (confirm 4GB). Install Docker: sudo apt update && sudo apt install -y docker.io docker-compose && sudo usermod -aG docker ubuntu && docker run hello-world | VM Running in OCI; SSH works; free -h shows 4GB swap; docker hello-world passes
Research: Network Security Concepts (connects to course) | Research & Planning | KHUSHBU JALAN | Not Started | 2026-04-06 | Research: What is a port? Why is 3389=RDP? What makes a port open vs closed vs filtered? Key ports: 22=SSH, 443=HTTPS, 3389=RDP, 80=HTTP. What is a firewall/NSG/Security List? What is Windows Event Viewer? Event ID 4625 (failed login) vs 4624 (success) — why do these matter? Create /research/Network_Security_Notes.md | research/Network_Security_Notes.md committed; covers ports, firewalls, Event IDs
Learn Nmap — Install + Understand All Key Flags | Research & Planning | KHUSHBU JALAN | Not Started | 2026-04-06 | Read nmap.org/book/man.html (Port Scanning Overview section). Open Kali VM → nmap --version (pre-installed). Learn: -sV (service versions), -O (OS detect), -A (aggressive), -p- (all ports), -oX (XML output), -oN (text output). What does 'open/closed/filtered' mean? Create /research/R2b_Nmap_Command_Reference.md listing every command with explanation | research/R2b_Nmap_Command_Reference.md committed; all flags documented
🏆 R1a — Write Incident Response Plan (Research-Based Report) | RUBRIC 1a ¦ Incident Response Plan | KHUSHBU JALAN | Not Started | 2026-04-07 | Create docs/R1a_IRP.docx. NOTE: This is a PLAN — will be tested in Month 2 when Wazuh is live. MUST INCLUDE: Attack Type = Brute-Force/Credential Stuffing (definition + example). Phase 1 DETECT: Wazuh monitors Event ID 4625, threshold 5 logins/60s = Level 10 HIGH alert, target <10s. Phase 2 CONTAIN: n8n calls OCI API to add IP to NSG Deny List, target <30s. Phase 3 ERADICATE: verify block, review for lateral movement, check FIM. Phase 4 RECOVER: review block after 24h, remove if false positive, update log | docs/R1a_IRP.docx committed with all 4 phases + attack type ✅
🏆 R1b — Write Security Policy (3 Rules + CIA Triad) | RUBRIC 1b ¦ Comprehensive Security Policy | KHUSHBU JALAN | Not Started | 2026-04-07 | Create docs/R1b_Security_Policy.docx. MUST INCLUDE 3 RULES: Rule 1 Access Control — all mgmt ports (22/443/5678/3000) restricted to your IP via OCI Security Lists. Rule 2 Log Retention — all security logs kept minimum 14 days in Wazuh Indexer. Rule 3 Encryption — TLS 1.2+ in transit, AES-256 at rest, SHA-256 for passwords. CIA TRIAD: Confidentiality = OCI NSG restricts access. Integrity = Wazuh FIM monitors files. Availability = 24/7 autonomous SOC uptime. | docs/R1b_Security_Policy.docx committed with 3 rules + CIA section ✅
🏆 R1d — Add Legal & Ethical Compliance Section to IRP | RUBRIC 1d ¦ Legal & Ethical Compliance | KHUSHBU JALAN | Not Started | 2026-04-07 | Open docs/R1a_IRP.docx → Add Section 5: Legal & Ethical Compliance. LAW 1: CFAA (18 U.S.C. §1030) — unauthorized computer access is a federal crime; our plan: monitor only our own OCI systems. LAW 2: GDPR Article 33 — 72-hour breach notification requirement; our IRP ensures detection is within hours. ETHICAL: Honeypot on our own infrastructure, no entrapment, responsible disclosure if real attacker found. | docs/R1a_IRP.docx Section 5 added: CFAA + GDPR + 1 ethical consideration ✅
🏆 R2b — Nmap Vulnerability Assessment Plan + Practice Scan | RUBRIC 2b ¦ Vulnerability Assessment | KHUSHBU JALAN | Not Started | 2026-04-08 | STEP 1: Run practice scan on Nmap's legal target: nmap -sV -O scanme.nmap.org -oN evidence/R2b_practice_scan.txt → screenshot output. STEP 2: Create docs/R2b_Vulnerability_Assessment_Plan.docx: Section 1 what is a vuln scan, Section 2 all Nmap commands to run on Honeypot with explanation, Section 3 what open ports mean (3389=CRITICAL), Section 4 asset discovery template, Section 5 paste + analyse the scanme.nmap.org practice scan results | evidence/R2b_practice_scan.txt (real Nmap output) docs/R2b_Vulnerability_Assessment_Plan.docx committed ✅
Kali Linux Skills Practice — Explore Security Toolkit | Learning & Skills | KHUSHBU JALAN | Not Started | 2026-04-08 | Open Kali VM → practice terminal commands: ls, cd, pwd, mkdir, cat, grep, nano. Network commands: ifconfig, ping google.com, netstat -tulnp, traceroute. Browse Applications menu — explore tool categories: Information Gathering, Web Analysis, Password Attacks, Social Engineering. Create /research/Kali_Tools_Overview.md: list 10 tools, what each does, when used ethically. Read about tool categories — do not run on external targets. | research/Kali_Tools_Overview.md committed; 10 tools documented
OCI: Create API Key + Document Tenancy Details | Infrastructure Setup | KHUSHBU JALAN | Not Started | 2026-04-08 | OCI Console → Identity & Security → Users → [your user] → API Keys → Add API Key → Generate Key Pair → Download private key (.pem) → note fingerprint. IMPORTANT: Save private key LOCALLY only — never commit to GitHub. Create configs/oci_setup_notes.md: document your Tenancy OCID, region, user OCID, API fingerprint. Note: will configure n8n OCI connection in Month 2 when SOAR is deployed. | OCI API key created; configs/oci_setup_notes.md committed (no private key in GitHub)
Research: How Wazuh Works — Deep Dive Before Deployment | Research & Planning | KHUSHBU JALAN | Not Started | 2026-04-09 | Read documentation.wazuh.com/current/getting-started. Focus on: agent → manager communication, what is ossec.conf, rules vs decoders, alert level scale (1-15), Level 10 = high severity, Wazuh Indexer (stores data), Wazuh Dashboard (visualizes). Watch 'Wazuh for beginners' on YouTube. Create /research/Wazuh_Deep_Dive.md: trace the full data path: Windows Event → Agent → Manager → alert → dashboard. Include draft custom rule XML for brute-force detection. | research/Wazuh_Deep_Dive.md committed; includes data flow + custom rule XML draft
Research: Risk Management Concepts (prep for R2d) | Research & Planning | KHUSHBU JALAN | Not Started | 2026-04-09 | Research: what is a risk register? What is CVSS scoring (0-10: Critical 9-10, High 7-8.9, Medium 4-6.9, Low 0-3.9)? How to calculate Likelihood × Impact = Risk Level? Read project Design Doc risks section. Identify 2 critical risks: Risk 1 = Open RDP T1021 (Likelihood HIGH, Impact CRITICAL), Risk 2 = Weak Auth T1110 (Likelihood HIGH, Impact HIGH). Create /research/Risk_Management_Notes.md with 2 critical risks drafted. | research/Risk_Management_Notes.md committed; 2 critical risks with MITRE IDs identified
Week 2 Wrap-Up: Commit All + GitHub Tag | Validation | KHUSHBU JALAN | Not Started | 2026-04-09 | VERIFY ALL FILES: docs/R1a_IRP.docx ✓, docs/R1b_Security_Policy.docx ✓, docs/R2b_Vulnerability_Assessment_Plan.docx ✓, evidence/R2b_practice_scan.txt ✓, all research docs ✓, OCI VM running ✓, OCI API key created ✓. Final commit: git add . && git commit -m 'Week 2 complete — 5 rubrics done (R1a R1b R1c R1d R2a R2b)' && git push && git tag -a week2 -m '66% rubric complete' && git push origin week2 | All files on GitHub; tag 'week2' created; 66% rubric complete
06 Apr 2026 to 09 Apr 2026
WEEK 3 ¦ 13 Apr – 16 Apr 2026 ¦ 🎯 Target: R2c + R2d Complete = 77% Rubric
Name | Subitems / Rubric Tag | Person | Status | Date | Notes / What to Do | Evidence File
Install OpenCTI via Docker Compose on OCI VM | Infrastructure Setup | KHUSHBU JALAN | Not Started | 2026-04-13 | SSH into OCI VM → mkdir ~/opencti && cd ~/opencti → download docker-compose from docs.opencti.io. Create .env file: OPENCTI_ADMIN_EMAIL=admin@soc.local, OPENCTI_ADMIN_PASSWORD=YourPass!, OPENCTI_ADMIN_TOKEN=[generate UUID via python3 -c 'import uuid; print(uuid.uuid4())']. docker-compose up -d → wait 15 min → add TCP 8080 to OCI Security List → access http://[OCI_IP]:8080 → login → screenshot dashboard | OpenCTI running at http://[OCI_IP]:8080; login works; screenshot committed
🏆 R2c — Configure 2 Connectors + Add 2 IoCs in OpenCTI | RUBRIC 2c ¦ Threat Intelligence + OpenCTI | KHUSHBU JALAN | Not Started | 2026-04-13 | CONNECTOR 1 — MITRE ATT&CK: Settings → Connectors → MITRE ATT&CK → Enable → screenshot showing Active/Running. CONNECTOR 2 — AbuseIPDB: Settings → Connectors → AbuseIPDB → enter API key → Enable → screenshot Active. IoC 1: Analysis → Observables → + Create → IPv4 Address → [bad IP from abuseipdb.com top abusers] → Labels: Brute-Force, Malicious. IoC 2: File SHA256 → 44d88612fea8a8f36de82e1278abb02f → Labels: Malware, EICAR-Test. Screenshot both IoCs in Observables. | 4 screenshots committed to evidence/R2c_*: 2 active connectors + 2 IoC entries ✅
Research: Docker Compose Deep Dive — Wazuh Stack Planning | Research & Planning | KHUSHBU JALAN | Not Started | 2026-04-14 | Study the Wazuh docker-compose.yml structure: what are the 3 containers (manager, indexer, dashboard)? What ports do they use? What volumes do they need? What environment variables are required? How do containers communicate on internal Docker network? Create /research/Wazuh_Docker_Plan.md: document the exact docker-compose.yml you will deploy in Month 2, with all services, ports, volumes, environment variables pre-planned. | research/Wazuh_Docker_Plan.md committed; full docker-compose.yml draft ready
🏆 R2d — Write Risk Register + Risk Monitoring SOP | RUBRIC 2d ¦ Risk Management | KHUSHBU JALAN | Not Started | 2026-04-15 | Using research from Week 2 Risk_Management_Notes.md. Create docs/R2d_Risk_Register.docx: CRITICAL RISK 1 = Open RDP Port 3389 (T1021.001), Likelihood HIGH, Impact CRITICAL, Treatment: Wazuh detection + n8n auto-block. CRITICAL RISK 2 = Credential Brute-Force (T1110), Likelihood HIGH, Impact HIGH, Treatment: 5-login threshold alert + auto IP ban. Residual risk LOW for both. Create docs/R2d_Monitoring_SOP.docx: Daily check Wazuh dashboard, Weekly review OCI NSG + disk usage <80%, Monthly re-run Nmap + update Risk Register. | docs/R2d_Risk_Register.docx (2 critical risks with MITRE IDs) docs/R2d_Monitoring_SOP.docx committed ✅
Week 3 Wrap-Up: Commit All + Evidence Check | Validation | KHUSHBU JALAN | Not Started | 2026-04-16 | VERIFY: OpenCTI running ✓, evidence/R2c_* screenshots (4 files) ✓, docs/R2d_Risk_Register.docx ✓, docs/R2d_Monitoring_SOP.docx ✓, research/Wazuh_Docker_Plan.md ✓. Final commit: git add . && git commit -m 'Week 3 complete — 7 rubrics done (+ R2c + R2d)' && git push && git tag -a week3 -m '77% rubric complete' && git push origin week3 | All files on GitHub; tag 'week3' created; 77% rubric complete
13 Apr 2026 to 16 Apr 2026
WEEK 4 ¦ 20 Apr – 23 Apr 2026 ¦ 🎯 Target: R2e Complete = 100% ALL 9 RUBRICS DONE 🎉
Name | Subitems / Rubric Tag | Person | Status | Date | Notes / What to Do | Evidence File
Research: n8n SOAR — Deep Dive + Workflow Planning | Research & Planning | KHUSHBU JALAN | Not Started | 2026-04-20 | Read n8n.io/workflows and docs.n8n.io. Understand: how does a Webhook node receive data? What is an HTTP Request node? What is an IF node (logic gate)? How does n8n connect to external APIs? Plan the full 5-node workflow: Webhook → Whitelist Check → AbuseIPDB lookup → IF score>50% → OCI NSG block. Create /research/n8n_Workflow_Plan.md with node-by-node diagram and JSON structure you will build in Month 2. | research/n8n_Workflow_Plan.md committed; full 5-node workflow planned
Research: Grafana + SOC Dashboard Design | Research & Planning | KHUSHBU JALAN | Not Started | 2026-04-20 | Read grafana.com/docs. Understand: data sources, panels, dashboards, Geomap visualization. Plan your 4 panels: World attack map (Geomap), Total alerts today (Stat), Top 10 attacking IPs (Table), Alerts by severity (Bar chart). Research: how does OpenSearch connect to Grafana as data source? Create /research/Grafana_Dashboard_Plan.md with panel sketches and data queries planned. | research/Grafana_Dashboard_Plan.md committed; 4 panels planned
🏆 R2e — Write Security Monitoring Use Case + Simulated IR Scenario | RUBRIC 2e ¦ Security Monitoring & Incident Response | KHUSHBU JALAN | Not Started | 2026-04-21 | Create docs/R2e_Use_Case.docx: Detection Rule Design (5 failed logins/60s = Level 10 HIGH alert), Alert Prioritization table (Level 10=immediate auto-response, Level 7-9=review in 1hr, Level 1-6=daily log), Step-by-step Response Procedure (5-step n8n pipeline). Create docs/R2e_IR_Scenario.docx with SIMULATED timeline: T+0s bot sends 5 failed RDP logins from 185.x.x.x → T+8s Wazuh alert → T+12s n8n triggers → T+16s AbuseIPDB score 94% → T+22s IP blocked. Include Classification (Brute-Force HIGH) + Lessons Learned. | docs/R2e_Use_Case.docx + docs/R2e_IR_Scenario.docx committed ✅
Final Month 1 Audit — All 9 Rubric Items Verified | Final Audit | KHUSHBU JALAN | Not Started | 2026-04-22 | Audit checklist: R1c scripts/encrypt_demo.py + screenshot ✓, R1a docs/R1a_IRP.docx (4 phases + attack type) ✓, R1b docs/R1b_Security_Policy.docx (3 rules + CIA) ✓, R1d IRP Section 5 (CFAA + GDPR + ethical) ✓, R2a docs/R2a_Threat_Analysis.docx + 3 evidence files ✓, R2b docs/R2b_Vulnerability_Assessment_Plan.docx + practice scan ✓, R2c 4 OpenCTI screenshots ✓, R2d Risk Register + SOP ✓, R2e Use Case + IR Scenario ✓. Create evidence/Evidence_Index.md listing every file + which rubric it satisfies. | evidence/Evidence_Index.md committed; all 9 rubric items verified present
Create Evidence ZIP + GitHub Release v1.0 — MONTH 1 COMPLETE | Final Delivery | KHUSHBU JALAN | Not Started | 2026-04-23 | ZIP evidence folder: zip -r DAE_SOC_Semester1_Evidence.zip docs/ evidence/ scripts/. Final commit: git add . && git commit -m '🎉 ALL 9 RUBRICS COMPLETE — Month 1 Final Semester 1' && git push. Create GitHub Release: git tag -a v1.0 -m 'All 9 rubrics complete — Semester 1 done' && git push origin v1.0. Verify OCI billing = $0.00 → screenshot as evidence/KPI_zero_cost.png. | DAE_SOC_Semester1_Evidence.zip committed; GitHub Release v1.0 tagged; OCI bill $0 confirmed 🎉
20 Apr 2026 to 23 Apr 2026
🎉 MONTH 1 COMPLETE ¦ ALL 9 RUBRIC ITEMS DONE ¦ Research Portfolio Ready ¦ OpenCTI Deployed ¦ GitHub Release v1.0