## 📅 Master Tracker
🛡 AUTONOMOUS CLOUD SOC — PROJECT TRACKER ¦ 31 MAR – 24 JUN 2026 ¦ Khushbu Jalan
MONTH 1 (Weeks 1–4): ALL Infrastructure Installed + ALL 9 Rubric Items Complete ¦¦ MONTHS 2–3 (Weeks 5–12): Optimization, Hardening & Documentation
🟡 RUBRIC MILESTONE 🩵 Infrastructure Task ✅ Complete 🔷 Optimize/Harden 🟣 Final Documentation ¦ 25% by Wk1 ¦ 50% by Wk2 ¦ 75% by Wk3 ¦ 100% by Wk4
# | Week | Date | Day | Task / Activity | Rubric Tag | Deliverable / Success Criteria | Phase | Status
◀◀ MONTH 1 ¦ MARCH – APRIL 2026 ¦ INFRASTRUCTURE INSTALLATION + ALL 9 RUBRIC ITEMS ▶▶
WEEK 1 — 25% RUBRIC TARGET ¦ 31 Mar – 06 Apr 2026
Rubric Progress: ▓▓▓░░░░░░░░░░░░░░░░░ 25% ¦ Completed: R1c, R2a(pt1)
1 | Wk 1 | 31 Mar 2026 | Tuesday | OCI Tenancy: Create VCN, Subnets, Internet Gateway, Security Lists (SSH → Your IP only) | INFRA FOUNDATION | VCN live; SSH accessible; note all OCIDs | Infrastructure | 🔲 To Do
2 | Wk 1 | 01 Apr 2026 | Wednesday | Provision A1 Ampere VM (4 OCPUs / 24GB RAM / Ubuntu 22.04) + 4GB Swap File | INFRA FOUNDATION | VM running; swap confirmed with 'free -h' | Infrastructure | 🔲 To Do
3 | Wk 1 | 02 Apr 2026 | Thursday | Install Docker + Docker-Compose; Harden OS (disable password SSH, enable ufw) | INFRA FOUNDATION | 'docker run hello-world' passes; ufw active | Infrastructure | 🔲 To Do
4 | Wk 1 | 02 Apr 2026 | Thursday | 🏆 R1c: AES-256 encrypt/decrypt demo + SHA-256 hash — encrypt_demo.py | RUBRIC 1c COMPLETE ✅ | Python script + terminal screenshot → commit to GitHub | 🏆 RUBRIC | 🔲 To Do
5 | Wk 1 | 06 Apr 2026 | Monday | 🏆 R2a: VirusTotal malware sample analysis + document detection results & behavioral indicators | RUBRIC 2a (Part 1) ✅ | VirusTotal report screenshot + findings doc | 🏆 RUBRIC | 🔲 To Do
WEEK 2 — 50% RUBRIC TARGET ¦ 07 Apr – 13 Apr 2026
Rubric Progress: ▓▓▓▓▓▓▓░░░░░░░░░░░░░ 50% ¦ Completed: + R1a, R1b, R1d
6 | Wk 2 | 07 Apr 2026 | Tuesday | Deploy Wazuh Manager via Docker Compose + SSL/HTTPS dashboard config | INFRA — Wazuh | Wazuh dashboard HTTPS on port 443; SSL cert active | Infrastructure | 🔲 To Do
7 | Wk 2 | 07 Apr 2026 | Tuesday | Install Wazuh Agent on Windows Honeypot; verify 'Active' status | INFRA — Wazuh Agent | Agent shows Active in Wazuh Manager | Infrastructure | 🔲 To Do
8 | Wk 2 | 08 Apr 2026 | Wednesday | Provision Windows Honeypot VM (Free Tier); open RDP 3389 to internet; verify Event ID 4625 logging | INFRA — Honeypot | Failed logins visible in Event Viewer | Infrastructure | 🔲 To Do
9 | Wk 2 | 08 Apr 2026 | Wednesday | 🏆 R1a: Write Incident Response Plan (detect brute-force, contain via NSG, eradicate, recover) + identify Brute-Force as attack type | RUBRIC 1a COMPLETE ✅ | IRP .docx with all 4 phases + attack type section | 🏆 RUBRIC | 🔲 To Do
10 | Wk 2 | 09 Apr 2026 | Thursday | Configure ossec.conf: Windows Event collection; Custom Rule — 5 failed logins/60s = Level 10 High Alert | INFRA — Wazuh Rules | Manual test triggers High alert in dashboard | Infrastructure | 🔲 To Do
11 | Wk 2 | 09 Apr 2026 | Thursday | 🏆 R1b: Write Security Policy (3 rules: access control, log retention, encryption) + CIA Triad section | RUBRIC 1b COMPLETE ✅ | Security Policy .docx — Confidentiality/Integrity/Availability covered | 🏆 RUBRIC | 🔲 To Do
12 | Wk 2 | 13 Apr 2026 | Monday | 🏆 R1d: Add Legal & Ethical Compliance section to IRP (CFAA + GDPR; ethical honeypot operation) | RUBRIC 1d COMPLETE ✅ | IRP updated with legal section; 2 laws + 1 ethical principle cited | 🏆 RUBRIC | 🔲 To Do
13 | Wk 2 | 13 Apr 2026 | Monday | Set Wazuh Indexer 14-day log retention policy; check RAM usage under 16GB | INFRA — Wazuh Config | Indexer retention confirmed; RAM monitored | Infrastructure | 🔲 To Do
WEEK 3 — 75% RUBRIC TARGET ¦ 14 Apr – 20 Apr 2026
Rubric Progress: ▓▓▓▓▓▓▓▓▓▓▓▓▓▓░░░░░░ 75% ¦ Completed: + R2a(pt2), R2b, R2c, R2d
14 | Wk 3 | 14 Apr 2026 | Tuesday | Deploy n8n (self-hosted) via Docker on OCI; configure user auth + Webhook URL | INFRA — n8n | n8n UI live on port 5678; webhook returns 200 OK | Infrastructure | 🔲 To Do
15 | Wk 3 | 14 Apr 2026 | Tuesday | Write Python integration script: Wazuh High Alert → n8n Webhook (JSON payload) | INFRA — SOAR Script | Script commits to GitHub; mock alert triggers n8n | Infrastructure | 🔲 To Do
16 | Wk 3 | 15 Apr 2026 | Wednesday | 🏆 R2a (Part 2): Create SET phishing template in Kali/Parrot OS + map APT29 to MITRE ATT&CK (T1078, T1021, T1110) | RUBRIC 2a COMPLETE ✅ | SET screenshot + ATT&CK Navigator JSON export | 🏆 RUBRIC | 🔲 To Do
17 | Wk 3 | 15 Apr 2026 | Wednesday | 🏆 R2b: Run Nmap scan on Honeypot (open ports, OS, services) + Asset Discovery doc | RUBRIC 2b COMPLETE ✅ | Nmap XML saved; asset inventory: IP, RDP 3389, services | 🏆 RUBRIC | 🔲 To Do
18 | Wk 3 | 16 Apr 2026 | Thursday | n8n: Add AbuseIPDB enrichment node (IP reputation check; block if score >50%) | INFRA — n8n Enrichment | API key stored; abuse score logged per alert | Infrastructure | 🔲 To Do
19 | Wk 3 | 16 Apr 2026 | Thursday | 🏆 R2c: Deploy OpenCTI via Docker; configure MITRE ATT&CK connector + AbuseIPDB connector; document 2 IoCs (malicious IP + file hash) | RUBRIC 2c COMPLETE ✅ | OpenCTI screenshot; both connectors active; IoC entries visible | 🏆 RUBRIC | 🔲 To Do
20 | Wk 3 | 20 Apr 2026 | Monday | n8n OCI Remediation node: call OCI API to add malicious IP to NSG Deny list | INFRA — Remediation | Test dummy IP blocked in OCI NSG | Infrastructure | 🔲 To Do
21 | Wk 3 | 20 Apr 2026 | Monday | 🏆 R2d: Build Risk Register (Critical Risk 1: Open RDP T1021; Critical Risk 2: Weak Auth T1110) + 1 Risk Monitoring Procedure (Wazuh threshold alerts) | RUBRIC 2d COMPLETE ✅ | Risk register .docx; monitoring SOP doc | 🏆 RUBRIC | 🔲 To Do
WEEK 4 — 100% RUBRIC COMPLETE ✅ ¦ 21 Apr – 27 Apr 2026
Rubric Progress: ▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓ 100% ✅ ¦ Completed: + R2e — ALL DONE
22 | Wk 4 | 21 Apr 2026 | Tuesday | Deploy Grafana container; connect to Wazuh/OpenSearch data source; create Attack World Map panel | INFRA — Grafana | GeoIP world map shows live attack sources | Infrastructure | 🔲 To Do
23 | Wk 4 | 21 Apr 2026 | Tuesday | 🏆 CRITICAL SAFETY: Build 'My IP' whitelist exclusion in n8n BEFORE full loop test | INFRA — Safety | Your IP excluded from block list; tested | Infrastructure | 🔲 To Do
24 | Wk 4 | 22 Apr 2026 | Wednesday | Full Loop Test: Brute-force attack → Wazuh alert (<10s) → n8n AbuseIPDB check → OCI NSG block (<30s) | INFRA — Full Pipeline Test | End-to-end latency logged; screenshot each stage | Infrastructure | 🔲 To Do
25 | Wk 4 | 22 Apr 2026 | Wednesday | 🏆 R2e: Document IR Scenario (brute-force classification, response steps, lessons learned) + Detection Use Case (rule, alert priority, response procedure) | RUBRIC 2e COMPLETE ✅ | IR after-action report; use case doc with alert screenshot | 🏆 RUBRIC | 🔲 To Do
26 | Wk 4 | 23 Apr 2026 | Thursday | File Integrity Monitoring (FIM) on C:\Windows\System32; Vulnerability scanner module enable | INFRA — Wazuh FIM | FIM alert triggered by test file change | Infrastructure | 🔲 To Do
27 | Wk 4 | 23 Apr 2026 | Thursday | OCI API & CLI config validation; test 'oci iam user list'; export n8n workflows to GitHub | INFRA — Config Backup | GitHub backup tagged v1.0 | Infrastructure | 🔲 To Do
28 | Wk 4 | 27 Apr 2026 | Monday | Grafana dashboard polish: color coding, 30s auto-refresh; export dashboard JSON to GitHub | INFRA — Dashboard | Dashboard JSON committed; refresh confirmed | Infrastructure | 🔲 To Do
29 | Wk 4 | 27 Apr 2026 | Monday | 🎯 MONTH 1 COMPLETE: ALL 9 RUBRIC ITEMS DONE ✅ — Audit evidence folder; verify $0 OCI billing | ALL RUBRICS COMPLETE ✅ | Evidence zip ready; OCI bill = $0.00 | ✅ 100% Done | 🔲 To Do
◀◀ MONTH 2 ¦ MAY – JUNE 2026 ¦ OPTIMIZATION, STRESS TESTING & HARDENING ▶▶
WEEK 5 — OPTIMIZATION BEGINS ¦ 28 Apr – 04 May 2026
30 | Wk 5 | 28 Apr 2026 | Tuesday | Stress test: 100+ concurrent RDP attempts → monitor CPU/RAM/swap usage | Optimization | Peak resource documented; swap utilization <80% | Optimization | 🔲 To Do
31 | Wk 5 | 29 Apr 2026 | Wednesday | Latency optimization: tune Python script + n8n execution time; target <10s detect, <30s block | Optimization | Latency log timestamps; optimize if >threshold | Optimization | 🔲 To Do
32 | Wk 5 | 30 Apr 2026 | Thursday | Error handling in n8n: set up failure notifications (email/Slack on workflow error) | Reliability | Failed workflow triggers alert within 60s | Optimization | 🔲 To Do
33 | Wk 5 | 04 May 2026 | Monday | Multi-vector Wazuh rules: PowerShell execution detection + MFA fatigue detection | Detection Expansion | 2 new custom rules; both tested manually | Optimization | 🔲 To Do
WEEK 6 ¦ 05 May – 11 May 2026
34 | Wk 6 | 05 May 2026 | Tuesday | System hardening: finalize firewall — only your IP reaches ports 22, 443, 5678 | Security Hardening | Nmap external scan confirms only allowed ports open | Optimization | 🔲 To Do
35 | Wk 6 | 06 May 2026 | Wednesday | Add Canary Tokens / fake admin credentials to Honeypot to detect human attackers | Advanced Detection | Canary token access triggers unique alert | Optimization | 🔲 To Do
36 | Wk 6 | 07 May 2026 | Thursday | Dynamic whitelisting: test self-service webhook for temporary IP whitelist | Feature Expansion | Webhook accepts IP, adds NSG allow rule, expires after 1hr | Optimization | 🔲 To Do
37 | Wk 6 | 11 May 2026 | Monday | Threat Intel Expansion: integrate GreyNoise API into n8n enrichment node | Threat Intel | GreyNoise tag (scanner/malicious) added to alert payload | Optimization | 🔲 To Do
WEEK 7 ¦ 12 May – 18 May 2026
38 | Wk 7 | 12 May 2026 | Tuesday | Automated Wazuh + n8n Docker container update script (cron-based) | Maintenance | Script runs; containers updated with zero downtime | Optimization | 🔲 To Do
39 | Wk 7 | 13 May 2026 | Wednesday | Log lifecycle: set up automated archiving to OCI Object Storage (cold tier) | Log Management | Logs >14 days auto-archived; disk stays <80% full | Optimization | 🔲 To Do
40 | Wk 7 | 14 May 2026 | Thursday | Test account reclamation prevention: confirm Honeypot stays active; OCI idle policy check | Risk Mitigation | VM last-active timestamp updated; no idle warning | Optimization | 🔲 To Do
41 | Wk 7 | 18 May 2026 | Monday | Grafana: add system performance metrics panel (CPU%, RAM%, disk I/O) | Dashboard Enhancement | Performance panel live alongside attack map | Optimization | 🔲 To Do
WEEK 8 — MID-PROJECT REVIEW ¦ 19 May – 25 May 2026
42 | Wk 8 | 19 May 2026 | Tuesday | OpenCTI: ingest brute-force incident data; create threat report in platform | Threat Intel Platform | OpenCTI threat report generated and exported | Optimization | 🔲 To Do
43 | Wk 8 | 20 May 2026 | Wednesday | Test storage bloat recovery: simulate disk near-capacity; verify auto-archive triggers | Reliability Test | Disk recovers below 80% after archive trigger | Optimization | 🔲 To Do
44 | Wk 8 | 21 May 2026 | Thursday | Vulnerability reassessment: re-run Nmap after hardening; compare to baseline | Vulnerability Mgmt | Closed ports confirmed; reduced attack surface documented | Optimization | 🔲 To Do
45 | Wk 8 | 25 May 2026 | Monday | Mid-project review: check all KPIs ($0, <10s, <30s); update risk register | Project Review | KPI dashboard green; risk register v2 committed | Optimization | 🔲 To Do
◀◀ MONTH 3 ¦ JUNE 2026 ¦ VALIDATION, DOCUMENTATION & FINAL DELIVERY ▶▶
WEEK 9 — FINAL TESTING PREP ¦ 26 May – 01 Jun 2026
46 | Wk 9 | 26 May 2026 | Tuesday | End-to-end pipeline re-test after all optimizations | Validation | Full loop test passes; latency within KPIs | Optimization | 🔲 To Do
47 | Wk 9 | 27 May 2026 | Wednesday | Documentation: write SOC architecture overview for portfolio | Documentation | Architecture doc with diagrams committed to GitHub | Optimization | 🔲 To Do
48 | Wk 9 | 28 May 2026 | Thursday | Documentation: write 'How the SOC Works' plain-English explainer (non-technical audience) | Documentation | 1-page explainer ready for DAE presentation | Optimization | 🔲 To Do
49 | Wk 9 | 01 Jun 2026 | Monday | Peer review / instructor checkpoint — share GitHub repo for feedback | Review | Feedback received; action items logged | Optimization | 🔲 To Do
WEEK 10 — PRESENTATION PREP ¦ 02 Jun – 08 Jun 2026
50 | Wk 10 | 02 Jun 2026 | Tuesday | Implement feedback from peer review; fix any gaps identified | Refinement | All feedback items closed; changelog updated | Optimization | 🔲 To Do
51 | Wk 10 | 03 Jun 2026 | Wednesday | Create final project presentation slides (SOC overview, architecture, live demo flow) | Presentation Prep | Slide deck ready; matches presentation PDF format | Optimization | 🔲 To Do
52 | Wk 10 | 04 Jun 2026 | Thursday | Record demo video: live attack → detection → blocking → Grafana dashboard | Portfolio Deliverable | MP4 demo ≤5 min; uploaded to GitHub/OneDrive | Optimization | 🔲 To Do
53 | Wk 10 | 08 Jun 2026 | Monday | Encrypt all sensitive config files in GitHub repo (API keys, OCI keys) | Security Hardening | No plaintext secrets in repo; .gitignore validated | Optimization | 🔲 To Do
WEEK 11 — FINAL EXPORTS ¦ 09 Jun – 15 Jun 2026
54 | Wk 11 | 09 Jun 2026 | Tuesday | Final stress test: 500+ requests; confirm no resource crash; verify swap headroom | Final Validation | No OOM kill; Wazuh stays responsive | Optimization | 🔲 To Do
55 | Wk 11 | 10 Jun 2026 | Wednesday | Export all n8n workflows (JSON); export Grafana dashboards (JSON); commit tagged v2.0 | Version Control | GitHub tag v2.0 created; all exports included | Final Docs | 🔲 To Do
56 | Wk 11 | 11 Jun 2026 | Thursday | Write maintenance guide: how to update, back up, and restore the SOC | Documentation | Maintenance guide .docx committed | Final Docs | 🔲 To Do
57 | Wk 11 | 15 Jun 2026 | Monday | Final documentation review: all rubric evidence compiled in one folder with index | Documentation | Evidence zip with index file ready for submission | Final Docs | 🔲 To Do
WEEK 12 — PROJECT COMPLETE 🎉 ¦ 16 Jun – 22 Jun 2026
58 | Wk 12 | 16 Jun 2026 | Tuesday | Final audit: OCI bill = $0.00 ✅ ¦ Detection <10s ✅ ¦ Remediation <30s ✅ | Final Evaluation | All 3 KPIs verified with screenshots | Final Docs | 🔲 To Do
59 | Wk 12 | 17 Jun 2026 | Wednesday | Submit all deliverables to DAE instructor: evidence zip + GitHub link + presentation | SUBMISSION | Submission confirmed; delivery receipt saved | Final Docs | 🔲 To Do
60 | Wk 12 | 18 Jun 2026 | Thursday | Go-Live: SOC running 24/7 autonomously; confirm Honeypot stays active | Go-Live | SOC live; monitoring dashboard bookmarked | Final Docs | 🔲 To Do
61 | Wk 12 | 22 Jun 2026 | Monday | 🎉 PROJECT COMPLETE — Portfolio ready ¦ Zero-Cost Cloud SOC operational | PROJECT DONE ✅ | LinkedIn post + portfolio update | Final Docs | 🔲 To Do

## 📋 Rubric Map
📋 ALL 9 RUBRIC ITEMS — COVERAGE MAP ¦ All completed in MONTH 1 (Weeks 1–4)
ID | Rubric Item | How SOC Project Covers It | Deliverable | Week | % Done
R1c | Apply Encryption Techniques | Python script: AES-256 CBC encrypt+decrypt + SHA-256 hash. Output screenshot shows plaintext ↔ ciphertext ↔ hash. | encrypt_demo.py + terminal screenshot | 1 | 25%
R2a (pt1) | Identify & Analyze Cyber Threats — Malware | VirusTotal malware sample analysis: detection results, behavioral indicators, potential impact documented. | VirusTotal report screenshot | 1 | 25%
R1a | Incident Response Plan | IRP covers brute-force (attack type). Phases: Detect (Wazuh Event 4625), Contain (OCI NSG block), Eradicate (deny rule), Recover (whitelist restore). | IRP .docx (4 phases + attack type) | 2 | 50%
R1b | Comprehensive Security Policy | 3 Rules: Access Control, Log Retention (14 days), Encryption. CIA Triad: Confidentiality (NSG), Integrity (FIM), Availability (24/7 SOC). | Security Policy .docx | 2 | 50%
R1d | Legal & Ethical Compliance | IRP section: CFAA (US) + GDPR (EU) cited. Ethical: responsible disclosure, no entrapment, lawful honeypot. | IRP legal section (2 laws + 1 ethical) | 2 | 50%
R2a (pt2) | Identify & Analyze Cyber Threats — Phishing + APT | SET phishing template in Kali/Parrot. APT29 mapped to MITRE ATT&CK: T1078 (Valid Accounts), T1021 (Remote Services), T1110 (Brute Force). | SET screenshot + ATT&CK Navigator JSON | 3 | 75%
R2b | Vulnerability Assessment | Nmap scan: open ports, OS detection, service versions on Honeypot. Asset discovery: Honeypot IP, RDP 3389, FIM paths documented. | Nmap XML + asset inventory doc | 3 | 75%
R2c | Threat Intelligence — OpenCTI + IoCs | OpenCTI deployed via Docker. 2 connectors: MITRE ATT&CK + AbuseIPDB. 2 IoCs: malicious source IP + file hash from brute-force event. | OpenCTI screenshots + connector config | 3 | 75%
R2d | Risk Management | Risk Register: Critical Risk 1 = Open RDP (T1021), Critical Risk 2 = Weak Auth (T1110), both with mitigations. Monitoring procedure: Wazuh threshold alerting SOP. | Risk Register .docx + monitoring SOP | 3 | 75%
R2e | Security Monitoring & Incident Response | Use case: brute-force detection rule (5 fails/60s→High alert), alert prioritization, response procedure. IR Scenario: full attack→alert→block→Grafana log→lessons learned. | Use case doc + IR after-action report | 4 | 100% ✅
✅ ALL 9 RUBRIC ITEMS COVERED AND COMPLETED WITHIN MONTH 1 (Weeks 1–4) ¦ 25% complete by end of Week 1

## ⭐ Week 1 Detail
⭐ WEEK 1 ¦ 31 MAR – 2 APR 2026 ¦ GOAL: Infrastructure UP + 25% Rubric Complete
By Thursday 2 Apr 2026 → OCI VM running + Docker installed + encrypt_demo.py committed to GitHub + VirusTotal malware report saved = R1c ✅ + R2a(pt1) ✅ = 25% RUBRIC DONE
Priority | Date | Day | Task — Step-by-Step | Success Criteria | Rubric Impact
🔴 INFRA | 31 Mar (Tue) | Tuesday | OCI Tenancy Setup • Login oracle.com/cloud/free • Create VCN (10.0.0.0/16) • Add public subnet + Internet Gateway • Security List: SSH port 22 → YOUR IP only • Note all resource OCIDs | VCN visible in OCI console SSH accessible from your machine | Foundation for all tools
🔴 INFRA | 1 Apr (Wed) | Wednesday | Provision A1 Ampere VM • Compute → Create Instance • Shape: VM.Standard.A1.Flex → 4 OCPUs / 24 GB RAM • OS: Ubuntu 22.04 • Add 4 GB Swap: sudo fallocate -l 4G /swapfile && sudo chmod 600 /swapfile && sudo mkswap /swapfile && sudo swapon /swapfile | VM running; 'free -h' shows 4GB swap 'uname -m' shows aarch64 | Foundation — hosts all tools
🟡 INFRA | 1 Apr (Wed) | Wednesday | Docker + Docker-Compose Install • sudo apt update && sudo apt install -y docker.io docker-compose • sudo usermod -aG docker $USER • Test: docker run hello-world • Disable password SSH: PasswordAuthentication no in sshd_config • Enable ufw: sudo ufw allow 22 && sudo ufw enable | hello-world container runs ufw status: active SSH key-only access confirmed | Foundation — runs Wazuh/n8n/Grafana
🌟 RUBRIC | 1 Apr (Wed) | Wednesday | 🏆 R1c — AES-256 + SHA-256 Demo • pip install pycryptodome • Create encrypt_demo.py: → AES-256-CBC: encrypt plaintext → ciphertext → Decrypt ciphertext → verify matches original → SHA-256 hash same plaintext string • Run script; screenshot terminal output showing all 3 • git commit -m 'R1c complete' && git push | Terminal shows: ✓ Plaintext → Ciphertext → Decrypted ✓ SHA-256 hash GitHub commit visible | ✅ RUBRIC 1c COMPLETE = first 11% of rubric
🌟 RUBRIC | 2 Apr (Thu) | Thursday | 🏆 R2a (Part 1) — VirusTotal Malware Analysis • Go to virustotal.com • Upload EICAR test file OR search public malware hash • Document: detection ratio, AV engine results, behavioral indicators, potential impact • Screenshot detection results page • Write 1-page findings doc: what it is, how it spreads, what damage it causes | VirusTotal screenshot saved 1-page malware findings doc written Both committed to GitHub | ✅ RUBRIC 2a (pt1) COMPLETE = 25% of rubric DONE
🎯 END OF WEEK 1: OCI Infrastructure Live ✅ ¦ Docker Running ✅ ¦ R1c Encryption ✅ ¦ R2a Malware ✅ = 25% RUBRIC COMPLETE

## 🗓 Month 1 Milestones
🗓 MONTH 1 MILESTONES ¦ 31 Mar – 30 Apr 2026 ¦ ALL 9 RUBRICS + ALL INFRASTRUCTURE
Week | Dates | Infrastructure Milestone | Rubric Items Completed | % Rubric Done | Phase
Week 1 | 31 Mar – 2 Apr | OCI VCN + A1 Ampere VM Docker + Docker-Compose 4GB Swap File OS Hardening (ufw, SSH keys) | ✅ R1c — AES-256 + SHA-256 Encryption Demo ✅ R2a (pt1) — VirusTotal Malware Analysis | 25% DONE | Phase 1
Week 2 | 6 – 9 Apr | Wazuh Manager (Docker) SSL/HTTPS Dashboard Wazuh Agent on Windows Honeypot Windows Honeypot VM (RDP open) Custom brute-force rule (5 fails/60s) | ✅ R1a — Incident Response Plan (IRP) ✅ R1b — Security Policy (CIA Triad) ✅ R1d — Legal & Ethical Compliance (CFAA+GDPR) | 50% DONE | Phase 2
Week 3 | 13 – 16 Apr | n8n SOAR (Docker) Python Wazuh→n8n integration script AbuseIPDB enrichment node OCI NSG remediation node OpenCTI (Docker) + 2 connectors | ✅ R2a (pt2) — SET Phishing + MITRE ATT&CK APT29 Map ✅ R2b — Nmap Scan + Asset Discovery ✅ R2c — OpenCTI + 2 IoCs ✅ R2d — Risk Register + Monitoring SOP | 75% DONE | Phase 2→3
Week 4 | 20 – 23 Apr | Grafana (Docker) + World Map Dashboard Full pipeline loop test (detect→block) File Integrity Monitoring (FIM) My-IP whitelist safety exclusion GitHub export (n8n JSON + Grafana JSON) | ✅ R2e — Security Monitoring Use Case + IR Scenario 🎉 ALL 9 RUBRIC ITEMS COMPLETE | 100% ✅ | Phase 3→4
Months 2–3 (Weeks 5–12): Optimization → Stress Testing → Hardening → Documentation → Final Delivery & Go-Live