## SOC Project Tracker
KHUSHBU JALAN — Cloud-Native Autonomous SOC & Threat Intelligence System
12-Week Execution Tracker ¦ Feb 2026 – Jul 2026 ¦ Owner: Khushbu Jalan
Phase | Week | Day | Task Name | Sub-task / Notes | Status | Date | Comments
PHASE 1: Foundations & Infrastructure
PHASE 1 | Week 1 | Mon | OCI Tenancy Setup & Networking | Create VCN, Subnets, and IGW |  | 2026-03-16
PHASE 1 |  | Tue | Provision A1 Ampere Instance | 4 OCPUs, 24GB RAM, Ubuntu 22.04 |  | 2026-03-17
PHASE 1 |  | Wed | Docker & Environment Hardening | Install Docker/Compose; Set up Swap File |  | 2026-03-18
PHASE 1 |  | Thu | Buffer: Security Group Config | Ensure SSH is restricted to your IP |  | 2026-03-19
PHASE 1 | Week 2 | Mon | Windows Honeypot Deployment | Provision Windows Server VM (Free Tier) |  | 2026-03-23
PHASE 1 |  | Tue | Honeypot 'Weakening' | Open RDP (3389) to the Public Internet |  | 2026-03-24
PHASE 1 |  | Wed | Initial Telemetry Check | Verify Event Viewer is recording failed logins |  | 2026-03-25
PHASE 1 |  | Thu | Buffer: OS Updates & Snapshots | Create a boot volume backup |  | 2026-03-26
PHASE 1 | Week 3 | Mon | OCI API & CLI Configuration | Create API Key for n8n to talk to OCI |  | 2026-03-30
PHASE 1 |  | Tue | Infrastructure Validation | Test connectivity between Windows and Linux |  | 2026-03-31
PHASE 1 |  | Wed | Documentation: Network Map | Map out IP flow and Port requirements |  | 2026-04-01
PHASE 1 |  | Thu | Buffer: Troubleshooting | Address any OCI 'Out of Capacity' errors |  | 2026-04-02
PHASE 2: Detection
PHASE 2 | Week 4 | Mon | Wazuh Manager Installation | Deploy Wazuh via Docker Compose |  | 2026-05-04
PHASE 2 |  | Tue | SSL & Dashboard Setup | Configure HTTPS certificates for Wazuh |  | 2026-05-05
PHASE 2 |  | Wed | Wazuh Agent Deployment | Install agent on Windows Honeypot |  | 2026-05-06
PHASE 2 |  | Thu | Buffer: Agent Connectivity | Verify 'Active' status in Wazuh Manager |  | 2026-05-07
PHASE 2 | Week 5 | Mon | Syslog & Event Collection | Configure ossec.conf for Windows Events |  | 2026-05-11
PHASE 2 |  | Tue | Custom Rule Creation | Define threshold: 5 failed logins = High Alert |  | 2026-05-12
PHASE 2 |  | Wed | Log Retention Policies | Configure Indexer to prune logs (14 days) |  | 2026-05-13
PHASE 2 |  | Thu | Buffer: Rule Testing | Trigger manual failures to test alerts |  | 2026-05-14
PHASE 2 | Week 6 | Mon | File Integrity Monitoring (FIM) | Monitor C:\Windows\System32 for changes |  | 2026-05-18
PHASE 2 |  | Tue | Vulnerability Detection | Enable Wazuh's vulnerability scanner module |  | 2026-05-19
PHASE 2 |  | Wed | Baseline Dashboarding | Clean up default Wazuh dashboard views |  | 2026-05-20
PHASE 2 |  | Thu | Buffer: Resource Monitoring | Check RAM usage of the Indexer/Dashboard |  | 2026-05-21
PHASE 3: Response & Automation
PHASE 3 | Week 7 | Mon | n8n Self-Hosted Deployment | Deploy n8n via Docker on the OCI instance |  | 2026-05-25
PHASE 3 |  | Tue | n8n Initial Config | Set up User Auth and Webhook URL |  | 2026-05-26
PHASE 3 |  | Wed | Wazuh Integration Script | Write Python script to push alerts to n8n |  | 2026-05-27
PHASE 3 |  | Thu | Buffer: Webhook Connectivity | Ensure Wazuh can 'reach' n8n internally |  | 2026-05-28
PHASE 3 | Week 8 | Mon | Enrichment: AbuseIPDB API | Add IP reputation check node in n8n |  | 2026-06-01
PHASE 3 |  | Tue | Logic Gate: Threat Scoring | Only block if Abuse Score > 50% |  | 2026-06-02
PHASE 3 |  | Wed | OCI Remediation Node | Build the 'Update NSG' API call in n8n |  | 2026-06-03
PHASE 3 |  | Thu | Buffer: Whitelist Safety | CRITICAL: Build the 'My IP' exclusion |  | 2026-06-04 | ⚠️ Critical
PHASE 3 | Week 9 | Mon | Full Loop Test: Brute Force | Attempt attack → Verify n8n triggers block |  | 2026-06-08
PHASE 3 |  | Tue | Debugging Latency | Optimize Python script and n8n execution time |  | 2026-06-09
PHASE 3 |  | Wed | Error Handling | Set up n8n notifications for failed workflows |  | 2026-06-10
PHASE 3 |  | Thu | Buffer: Remediation Testing | Ensure the IP is actually dropped by OCI |  | 2026-06-11
PHASE 4: Visualization & Optimization
PHASE 4 | Week 10 | Mon | Grafana Installation | Add Grafana container to the stack |  | 2026-06-15
PHASE 4 |  | Tue | Data Source Connection | Connect Grafana to Wazuh (Indexer/OpenSearch) |  | 2026-06-16
PHASE 4 |  | Wed | Geospatial Mapping | Create 'Attack World Map' based on IP logs |  | 2026-06-17
PHASE 4 |  | Thu | Buffer: Dashboard Polish | Fix color coding and refresh rates |  | 2026-06-18
PHASE 4 | Week 11 | Mon | Stress Testing | Simulate 100+ requests to check CPU spikes |  | 2026-06-21
PHASE 4 |  | Tue | Feature: Canary Tokens | Place 'fake' creds to detect human intruders |  | 2026-06-22
PHASE 4 |  | Wed | Multi-Vector Rules | Add rules for PowerShell execution/malware |  | 2026-06-23
PHASE 4 |  | Thu | Buffer: System Hardening | Finalize firewall rules for the SOC itself |  | 2026-06-24
PHASE 4 | Week 12 | Mon | Final Project Review | Audit against 'Zero Cost' & '30s Latency' |  | 2026-06-29
PHASE 4 |  | Tue | Export Configuration | Export n8n JSONs and Grafana Dashboards |  | 2026-06-30
PHASE 4 |  | Wed | Final Documentation | Record 'How-To' for future maintenance |  | 2026-07-01
PHASE 4 |  | Thu | 🎯 PROJECT COMPLETION | Go-Live / Handover | COMPLETE | 2026-07-02 | ✅ Done

## Legend & Instructions
LEGEND
Color | Meaning
Dark Navy Header | Project Title Row
Phase Blue | Phase section header
Light Blue row | Alternate data rows
Green row | Completed task
STATUS VALUES
(blank) | Not started / In Progress
COMPLETE | Task finished
COLUMNS
Phase | High-level phase label
Week | Week number
Day | Day of week
Task Name | Primary task
Sub-task / Notes | Detail or instruction
Status | Current status
Date | Planned execution date
Comments | Flags, warnings, notes